## DR_Prod_Prep_Checklist
Area | Type |  |  |  |  | Req for Phase 2 (Planned Cutover)? | Req for Phase 3 (DR simulation)?
Infrastructure | Equipment | LV7 Equipment | DC-Ops | [5 empty] | 2013-03-07 | 2013-03-07
Infrastructure | Management | Puppet | Core |  | No | Yes | Yes | Yes | DONE | DONE | Yes | No | Yes | https://confluence.inside-box.net/display/ETO/Puppet+Infrastructure | https://confluence.inside-box.net/display/ETO/Pushing+Puppet
Foo | Bar |  |  |  |  | Yes | Yes
[6 empty] | Yes | Yes
Infrastructure | Management | Veeam | Core |  | No | No | No | Yes | N/A | N/A | No | No | No
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
Data Replication | Services | Jira | IT |  | No | No | Yes | Yes | N/A | N/A
Data Replication | Services | Confluence | IT |  | No | No | Yes | Yes | N/A | N/A
Data Replication | Services | AD | IT |  | No | No | Yes | Yes | N/A | N/A
Data Replication | Services | LDAP (Slaves as backup) | Core |  | No | Yes | Yes | Yes | DONE | DONE | Yes | No | Yes | https://confluence.inside-box.net/display/ETO/OpenLDAP | https://confluence.inside-box.net/display/ETO/OpenLDAP
Data Replication | Services | BoxNotes | SRE |  | No | No | Yes | Yes | N/A | N/A | [5 empty] | Blocked on DC-OPS HW
[6 empty] | Yes | Yes
Data Replication | Services | Content Workflow | SRE |  | No | No | Yes | Yes | N/A | N/A | [5 empty] | Blocked on DC-OPS HW
[6 empty] | Yes | Yes
|  | X2 Replacement for LV7 | NetOps |  | No | Yes | Yes | Yes | ? | ?
|  | Replace Bad Links | NetOps |  | No | Yes | Yes | Yes | ? | ? | No | No | No
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
Infrastructure | Management | Deployment scripts (daemon) | SRE | Robert | No | Yes | Yes | Yes | 2013-03-22 |  | Yes |  | No |  |  | DM works fine, DD needs to be tested
Infrastructure | Management | Deployment manager (Scala) | SRE | Robert
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
Access | OOB |  | NetOps |  | No | Yes | Yes | Yes | N/A | N/A | Yes | ? | ?
Access | Management | Bastion | Core |  | No | No | Yes | Yes | N/A | N/A | Yes | No | Yes | https://confluence.inside-box.net/display/ETO/Bastion+Architecture | https://confluence.inside-box.net/display/ETO/Bastion+Runbook
Access | Juniper VPN |  | Security |  | No | No | Yes | Yes |  | ?
Access | Authentication | RSA/Duo | Security |  | No | No | Yes | Yes |  | ?
Access | Authentication | LDAP Master in LV7 | Core |  | No | No | Yes | Yes | N/A | N/A
Access | Authentication | AD | IT |  | No | No | Yes | Yes | N/A | N/A
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
Documentation | OOB Access (Verification) |  | DR Coordinator |  | No
Documentation | Confluence (Verification) |  | DR Coordinator |  | No
Communication | Phone |  | IT |  | No | No | BCP | BCP | N/A | N/A
Communication | Jabber |  | IT |  | No | No | Yes | Yes | N/A | N/A
[6 empty] | Yes | Yes
3P | Bandwidth Providers |  | NetOps |  | No | Yes | Yes | Yes | N/A | N/A | Yes
[6 empty] | Yes | Yes
Dev Envs | Bug Fixes | Dev pod for minimum use case | SRE |  | No | Yes | Yes | Yes | N/A | N/A | [5 empty] | Need to order HW
Access | Palo Alto Firewalls | PA200 | Security |  | No | No | Yes | Yes |  | ? | Yes | Yes
Access | Palo Alto Firewalls | PA5020 | Security |  | No | No | Yes | Yes |  | ? | Yes
Access | Firewall | Connections PA5020 + dependent devices | NetOps |  | No | No | Yes | Yes | N/A | N/A
[6 empty] | Yes | Yes
Infrastructure | Monitoring | SMS | Core |  | No | Yes | Yes | Yes | DONE | DONE | [5 empty] | Andrew Gaffney / OPS-22345
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
Data Replication |  | CorpDB | DB |  | No | No | Yes | Yes | N/A | N/A
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
[6 empty] | Yes | Yes
Access |  | IA access (in LV7) from ECR | Security |  | No | Yes | Yes | Yes | 2013-03-08 | 2013-03-08
[6 empty] | Yes | Yes
|  | Install additional 10g base T switches for PAN 5020 | DC-Ops |  |  | Yes
[6 empty] | No | No
|  | Creation of production SIDs for LV7 filers | Storage |  | No | Yes | Yes | Yes | 2013-03-29 | 2013-03-29
[6 empty] | Yes | Yes
|  | App_Conf update after storage IDs built | Storage |  | No | Yes | Yes | Yes | 2013-04-07
\