Project Scotian Sanctuary – Project Plan

Project Scotian Sanctuary

Introduction to Project Management (MGT 5164)

Submitted by: James Ouzas

Submitted on: July 24th, 2017

All material prepared for this assignment was produced by the author(s), and material from a third party (such as the internet) has been cited and referenced.

Table of Contents

Project Introduction Section	2

Project Background	2

Project Scope	2

Project Work Breakdown Structure	2

WBS Dictionary	2

Project Schedule	2

Gantt Chart	2

Network Diagram	2

Risk Management Plan	2

Quality Management Plan	2

Communication Management Plan	2

Human Resource Management Plan	2

Budget Plan	2

References	2

# Project Introduction Section

## Project Background (5)

This project involves construction of a home with many lake facing windows on a remote, unexcavated lakefront lot at Bert’s Lane, Newburne, Nova Scotia. The home must be connected to local infrastructure, and supply the basic needs of a shelter. Total cost of excavation and construction is not to exceed $300,000, home must be habitable by October 2017, and several teams of contractors will be expected to work on site simultaneously to meet deadlines. Each contractor will be required to supply their own work materials, accounted for by fixed-price budgeting contracts. The home is subject to final inspection and must pass for project completion.

## Project Scope (5)*

The outcome of this project is to deliver a well-built home on a previously unexcavated lakeside site designed for two people. The home and land will be habitable for October 2017. The home will fulfill the needs specified by the project sponsor to match their description of their dream home as closely as possible, and surrounding land must be preserve during construction to maintain integrity and beauty of landscape.

## Project Work Breakdown Structure (Hierarchical) (5)

- Dream Home Project

  - Landscape

    - Task A

    - Task B

    - Task C

  - House Structure

    - Task D

    - Task E

    - Task F

  - Inside Work

    - Task G

    - Task H

    - Task I

  - Infrastructure

    - Task J

    - Task K

    - Task L

  - Management

    - Task M

    - Task N

    - Task O

  - Other

    - Inspection

    - Milestone #1

    - Milestone #2

## WBS Dictionary (15)

## Task Name

Foundation Mixing and Implementation

## Task Assumptions

- Concrete will mix properly and set accordingly

  - Failure to mix properly or set properly would increase time to complete plan and will increase costs

- Foundation will meet the dimensions of the house plan

  - improperly sized base to the home will contribute to structural integrity issues in other parts of the home, increasing cost and decreasing longevity

- There will be an appropriate amount of material to complete the foundation

  - Will result in delays while more materials are secured

- Foundation will be durable and meet building inspection codes for this area

  - Could result in re-pouring of foundation which would exaggerate costs exponentially, and would also result in more costs to destroy and remove the poorly engineered foundation

## Task Constraints

- Weather

  - Rainy weather could push back completion of the foundation of the home as the concrete will not set properly in the rain

- Fixed Price Contract

  - Each contractor hired on this project has been allocated a fixed price contract, so their overall budget should be within contract stipulations

- Deadline for foundation completion

  - Should the foundation not be completed in time, the rest of home may not be completed on schedule as well, as the foundation is the base of the home, and construction cannot continue until this is well-established

- Remote location (equipment transportation and equipment type)

  - This will increase fuel costs to transport equipment to the site and could result in limitation of the equipment pool – some heavy equipment may not be able to make it to site and the contractor may need to choose lighter options increasing overall time to complete the foundation

## Task Project Requirements

- Contractor be provided accurate blueprints to estimate amount of material and dimensions of the foundation to be completed

- Transport of materials not to damage temporary road for other machinery

- Task be completed on budget or under budget to preserve project integrity

- Task to be completed on time or earlier to preserve deadlines for the rest of the project

## Task Quality Standards

- Completed foundation be able to support additional weight and structure of the home to be built

- Finished product must meet or exceed the expectations of both the project sponsor and the home inspector

## Task Deliverables

- Transport materials to site

  - transport mixing machinery, dry concrete, and water trucks to remote excavation site

- Mix concrete

  - Mix appropriate quantity of wet concrete, establish the proper consistency of concrete for successful pouring and setting of end product

- Pour concrete

  - Pour concrete in correct dimensions and density to meet requirements of home and area building codes

## Task Mandatory Dependencies

- Excavation site must be able to accommodate dimensions of concrete to be poured

- Temporary road to building site must be established

## Task External Dependencies

- City Hall and Permit offices

  - Permits to excavate and build on this land must be applied for and secured

- Equipment Rental Companies

  - Availability of heavy machinery if contractor does not own appropriate equipment and rents on demand

# Project Schedule

## Gantt Chart (10)

## Critical Path (Network) Diagram (10)

# Risk Management Plan (10)

## Overall Risk Plan Prioritization

Project Quality

Quality must be prioritized on this project. Should the home not be constructed up to quality standards the home will never pass final inspection. This could result in expensive renovations which would drastically increase the project end date (meeting the October deadline is already tight-schedule concern)  and would require more materials (budget concerns).

Additionally, it would be easier to recover from budget related issues without issue to quality by securing more capital through loans. Should schedule not be adhered to and the deadline not met, the client could always find temporary residence. Both solutions are easier to implement than those to fix quality issues.

## Contingency Fund and Managerial Reserve Fund*

- Contingency Reserve Fund

  - Areas of concern for supplemental funding (if needed)

    - $20,000 for concerns related to site stability and road maintenance should heavy weather occur

    - $10,000 for concerns due to appreciable human error on measurements, fabrications, and implementation

- Managerial Reserve Fund

  - Unforeseen work

    - $10,000 for bedrock blasting should excavation not be easily excavated

## Risk Registry

| WBS | Risk # | Title/Description | Likelihood | Impact | Strategy | Response |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 Landscape | 3 | Temporary road damages site | High – some damage is expected from machinery | Moderate – could negatively affect finished product (quality) | Transfer – contractors will be required to return road to initial site quality | Insurance policies – insure site for damages before beginning construction |
| 1.2 House Structure | 1 | Home not structurally sound | High – human error is likely, site is in flux | Very High (increases costs, duration, scope) | Mitigate – ensure all measurements are correct – plan accordingly | Contingency Funds – plan for some errors in measurement and implementation |
| 1.3 Inside Work | 4 | Wrong Colour Paint or material used | Low – contractor should be able to match paint requirement | Moderate – only contributes to additional cost and schedule | Transfer – responsibility of contractor | Insurance Policy – contractor would be held to contract |
| 1.4 Infrastructure | 2 | Poor/No Electricity or Water | Low – likely this would have been cleared with respective utilities | High – Has potential to make this house inhabitable, affects quality, schedule and cost | Accept – Utilities will have the best indicator of what can be supplied at the lot | Management Reserve Funds - Rare circumstance that likely won’t occur but will require finances to fix |
| 1.5 Management | 5 | Lack/lapses of oversight and scheduling | Moderate – tight scheduling constraints with many contractors on site at once | High – improper scheduling could lead to higher costs, and potential quality issues | Mitigate- prepare rigid schedule, prepare contractors for hectic environment | Buffers – have assistant managers to increase oversight |
| 1.6 Other | 6 |  |  |  |  |  |

# Quality Management Plan (10)

## Quality Control Checklist – Foundation Mixing and Implementation

|  | Verify blueprint dimensions and excavation dimensions with the project sponsor and on-site engineers at excavation site before mixing concrete |
| --- | --- |
|  | Determine geologic composition of access road and approximate weight the road can support based on previous construction cases to avoid environmental and machine damage |
|  | Choose equipment according to weight road can support using machine manuals |
|  | Schedule equipment access to avoid exceeding estimated capacity of road at a given instance |
|  | Mix 1.75/1 Concrete to Water mix to meet ideal consistency and optimal costs for quality |
|  | Use Concrete to Water ratio to estimate total amount of mix needed - calculate actual amount used to account for loss and evaluate for improvement |
|  | Calculate amount of time concrete takes to set for dimensions of this project and current weather – measure actual time taken to cure and evaluate differences for improvement in future estimation. Can also be achieved by curing a test portion |
|  | Load test small segments of the foundation to ensure it meets structural load demands |
|  | Stress (hammer)test key structural points with with blunt force device for minor structural damage – indicative of air pockets |
|  | Compare dry concrete colour and consistency to that chosen by project sponsor via colour mix specifications according to manufacturer |

This overall task quality management plan could be easily applied to the overall picture of the project. This checklist relies on some basic principles in that it is:

- structured in order of practical completion and evaluation

- is based on quantitative measurement to assess proper completion

- relies on the input of experts to asses what is possible

- has the interests of the client as a core guiding principles

- identifies ways to improve and better estimate processes in the future

This checklist could also be incorporated as a plan within the project quite easily as it does flow in logical succession and allows for key requirements such as structural integrity, preservation of the landscape, and colour requirements to be assessed before construction of the home. The checklist also establishes key checkpoints for quality assessment to ensure the plan will be completed up to standards and requirements.

# Communication Management Plan for Foundation Mixing and Implementation (10)

| Stakeholder communication requirements | Information to be communicated | When and how frequently the information will be communicated | Who will send the information | How the information will be communicated | Who will receive the information |
| --- | --- | --- | --- | --- | --- |
| Housing Blueprints | Technical diagrams containing dimensions of the desired structure | Ideally once, when the design has been finalized. | Client or design engineer | Paper diagram, digital back up copies | All personnel |
| Lessons Learned | Concrete curing time estimation vs. Actual time, concrete to water mixture losses | Twice, when the foundation has cured, and when the final concrete mix is completed | Masonry team | Spreadsheets indicating estimates vs. Actual times, % yield for concrete mix | PM, lead masonry contractor |
| General Updates | Basic milestone completion, weather for the week | Weekly, and as each milestone is reached | PM | Email | All stakeholders |
| Project Reports | Materials used, dollars spent, man hours worked | Daily | Lead Contractors | Spreadsheets | PM |
| Client Feedback | Satisfaction or approval of recently completed work | As milestones are reached | Client | Direct verbal feedback | PM directly, contractor leads through the PM |

# Human Resource Management Plan (10)

## Team Organizational Chart

PM

House Structure

Lead

Landscape

Lead

Interior

Lead

Infrastructure

Lead

Management

Landscape

Team

House

Structure

Team

Interior

Team

Infrastructure

Team

Managment

Team

Relevant

Contractors

## Member of Organization and their Roles, Responsibilities, and Authority on project

Infrastructure Lead

Roles

- Lead contact for infrastructure related inquiries (water, electricity, phone)

- Known formally as Lead Utility Engineer

- Has authority over infrastructure team, and any additional random contractors hired

Responsibilities

- Organize and administrate the infrastructure team

- Co-ordinate team to complete complex plans

- interpret complex plans and meet demands of the plan

- Hire additional team members or acquire additional equipment as required

Authority

- Equal authority to other lead contractors

- has ability to spend money, apply resources, and acquire materials as needed to connect home to infrastructure

- leads the infrastructure team and associated contractors, work within project demands

- Gives final approval and signs all documents associated with infrastructure work

## RACI (RAM)

| Task | Landscape Lead | House Structure Lead | Interior Lead | Infrastructure Lead | Management | Landscape Team | House Structure Team | Interior Team | Infrastructure Team | Management Team |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Prepare Land 1.1) | A | C | I | C | C | R | I | I | I | I |
| Prepare Foundation and Frame (1.2) | C | A | C | C | C | I | R | I | I | I |
| Floors and Walls (1.3) | I | C | A | I | C | I | C | R | I | I |
| Connection to Utilities (1.4) | C | C | C | A | C | I | I | I | R | I |
| Oversight and organization (1.5/1.6) | C | C | C | C | R | I | I | I | I | A |

(R)	Responsible		The one who does the task

(A)	Accountable		The one who is responsible for the task

(C)	Consulted		Those who are kept in the loop

(I)	Informed		Those informed, but not consulted

## Solutions for Team Ground Rules (9.3.2.4)

In the context of this project  - specifically where may contractors occupy the same space at once, it will be important to designate a process to determine who ‘s presence will take precedence in or around the home at a given moment. For example, the infrastructure team should not take precedence over the house structure team in a given area if there is no house  - the infrastructure team would have nothing to connect and would not be able to practically use the space.

Determining a set of steps to determine what is the best team to be in a current space at a time will have the added benefit of making the team more productive, and will decrease the amount of oversight required to manage the team.

The project manager should also call together all team member at the start of the project to ensure that they understand they’re really just part of the big picture and that they’re all working towards the same goal to minimize negative effects of internal competition.

# Budget Plan(6)

The budget plan allocates 500$ to each duration (labour) and assigned resources (materials) to each Level 3 WBS task. It also takes into account the additional contingency reserves included in case of emergency or other unknowns.

| WBS# | Allocated Funds |  | Total |
| --- | --- | --- | --- |
|  | Material | Labour |  |
| 1.1.1 Task A (Landscape) | 1000 | 1000 | 2000 |
| 1.1.2 Task B | 1000 | 2500 | 3500 |
| 1.1.3 Task C | 3000 | 1500 | 4500 |
| 1.2.1 Task D (House Structure) | 2500 | 500 | 3000 |
| 1.2.2 Task E | 4000 | 500 | 4500 |
| 1.2.3 Task F | 2000 | 1000 | 3000 |
| 1.3.1 Task G (Inside Work) | 2000 | 1500 | 3500 |
| 1.3.2 Task H | 2000 | 4000 | 6000 |
| 1.3.3 Task I | 1000 | 500 | 1500 |
| 1.4.1 Task J (Infrastructure) | 2500 | 1500 | 4000 |
| 1.4.2 Task K | 1500 | 3000 | 4500 |
| 1.4.3 Task L | 1500 | 1000 | 2500 |
| 1.5.1 Task M (Management) | 2000 | 2000 | 4000 |
| 1.5.2 Task N | 1000 | 500 | 1500 |
| 1.5.3 Task O | 2000 | 4000 | 6000 |
| 1.6.1 Inspection (Other) | 1000 | 1000 | 2000 |
| 1.6.2 Milestone #1 |  |  |  |
| 1.6.3 Milestone #2 |  |  |  |
| Risk Management Reserve |  |  | 30000 |
| Risk Contingency Reserve |  |  | 10000 |
|  |  |  | 96,000 |

# References